r. 4-11-15

# Guidelines, Checklist, and Contract Clauses for Government Acceptance 
of DOE IDIQ ESPC Projects

  ECM Installation:  All energy conservation measures (ECMs) are installed in accordance with plans, specifications, standards, and other contract documents (sometimes by the contractor, often by a subcontractor and always over a period of months).

  Inspection, start-up, testing, and commissioning.  All ECMs are inspected, brought on line, tested, and commissioned interactively with all related government-owned or contractor-installed ECMs. The ECMs should be operating in accordance with the design, plans, specifications, standards, and other contract documents and manufacturers’ recommendations. Any interrelated ECMs must all be installed prior to commissioning any of them. Individual ECMs may be started up and tested individually. The contractor should be involved in the final inspection and commissioning process along with their subcontractors. The agency contracting officer’s technical representative (COR) should accompany the contractor on these inspections and document in writing that he has witnessed the inspections.

Note: An agency may have more rigorous test and acceptance procedures defined in the Task Order.

  Punch list generation.  A punch list is generated during inspection to document deficiencies or items that need to be fixed, and punch list items are corrected.

Note:    Individual ECMs may be signed off by the COR as they are installed (partial acceptance), but “sign-off” by a COR doesn’t constitute official government acceptance of the ECM or the project. It acknowledges completion of the installation of that ECM and perhaps activates the warranty.  Agencies should use due diligence prior to signing off on individual ECMs as the 30-day performance period usually hasn’t yet occurred.

  30-day Performance Period.   Upon completion of the above items for the last installed ECM, the contractor writes a letter to the ACO asking for the 30-day performance period to begin (assuming all significant punch list items have been corrected).  Other discrepancies may appear during this period.  The contractor should have them all corrected by the end of the 30-day period. If the discrepancy has the potential to reappear or if another 30-day period is warranted because of the criticality of the ECM, the ACO has the right to ask for continuation of the performance period.

Note:  Even if individual ECMs have been operating successfully after installation for several weeks or months, all ECMs are included in this “official” 30-day performance period.

5.  Final submittals.

Operation and maintenance manuals are provided.

Operation and maintenance training is provided.

Spare parts are provided or spare parts lists are provided.

As-built drawings are provided.

Commissioning Report is reviewed and approved.

Post Installation M&V Report is reviewed and approved.

Utility rebate inspections and paperwork is approved and submitted.

Note:  All this can happen during the 30-day performance period or as individual ECMs are installed.  Punch list items that do not relate to system and equipment performance are often handled during this period also.

6.  Measurement and Verification.  Post-installation measurements are taken and M&V protocols are in place; a post installation M&V report is generated based on the M&V plan submitted and approved.

Note: The IDIQ contract requires the post-installation M&V report to be submitted prior to acceptance of the project.  If the delivery order does not require it prior to acceptance, it should come in within 30-60 days after project completion.

7.  Agreement on modifications/change orders.  During construction there may be changes that occur to the work scope.  Some are government-requested changes and some are contractor-generated.  It must first be determined whether the “change” is already within the scope of what the contractor covered in their proposal as contracted.  Any changes to the TO amount, savings, payment schedule, etc., must be agreed upon and documented in a modification to the TO.  The modification should be ready by the time of final acceptance.

Note: Both the government and the contractor should track all changes made during TO implementation. Although TO modifications for significant changes should be negotiated as soon as possible, it may be feasible to do one modification to the TO for all minor changes agreed to prior to accepting the project. It is important that the contractor and government come to agreement quickly so that payments are not unduly delayed.

8.  Final contractor/government inspection.  One final walk-through should be conducted with the contractor and government representative.  The ECMs should be fully operational, without bugs, and all other deliverable items should have been provided.  The Acceptance Checklist (see below) is noted with dates for each item, and signed off by the COR and forwarded to the agency CO.

9.  Government Acceptance.    After the COR signs and submits the checklist, the agency CO also signs the checklist, writes a letter to the contractor accepting the project, enclosing a copy of the checklist, and stating that invoices may be submitted as contracted.  The agency CO may also modify the TO to document acceptance and the starting date of the annual performance period. One copy of the checklist is sent to DOE with a copy of the letter.

Note 1:    It is an agency decision as to when they feel the project can be accepted.  The process above outlines an approach consistent with the IDIQ contract with the project acceptance for all ECMs occurring at one point and invoicing starting after complete project acceptance.

Note 2: Partial acceptance(s) of a project may be warranted or desirable, which would allow for accepting buildings or ECMs as completed, with complete project acceptance after all ECMs are complete  This accommodates  invoices through the construction period for those EMCs that are generating savings that have been accepted. For example, projects with one or two ECMs with very long construction periods and others having shorter construction periods, projects with different sites involved, or projects with exceptionally long construction periods (over 18 months) may benefit from partial payments in order to reduce interest expense.  Any alternative acceptance method must be documented and agreed to in the proposal and the awarded TO in Paragraph G.3, as it is affects the payment schedule, construction financing, and interest payments.

10.  Invoicing.   The contractor may invoice as specified in the contract starting immediately after receiving government acceptance.

Note: Agencies have sometimes agreed to making payments on a monthly, quarterly, or annual basis, or combination of such.  This is to reduce the administrative burden of making payments and may reduce the amount of interest paid.  The invoicing arrangement must be agreed upon and documented in Paragraph G.3.1 of the RFP/TO.

Checklist for Government Acceptance of Completed Project

_________	All ECMs have been installed.

_________	All ECMs have been through inspection, start-up, testing, and interactive commissioning.

_________	Commissioning Report reviewed and approved.

_________	All discrepancies noted have been corrected.

_________	Appropriate training on operations and maintenance (O&M) was conducted for each ECM

_________	O&M manuals and procedures have been provided.

_________	Recommended spare parts lists and spares have been provided.

_________	As-built drawings have been received and approved.

_________	Documentation of government witnessing of M&V activities completed.

_________	Post-installation M&V report received and approved.

_________	Utility rebate inspections and paperwork approved and submitted.

_________	Manufacturer warranty and registration paperwork submitted.

_________	All ECMs have performed properly for 30 days as of ___________.

_________	Government final inspection and acceptance is confirmed as of ____________.

______________________    ________		 _______________________    _________

Government Technical Rep     Date	 	  Agency Contracting Officer        Date

DOE ESPC IDIQ Contract Clauses Pertaining to 
Commissioning, Inspection, Acceptance, and Payments

SECTION C M&V SUBMITTALS AND ECM COMMISSIONING

C.4.6   M&V Submittals During TO Development and Post Award

C.	The contractor shall prepare and submit a post-installation report to the agency (Attachment J-9), which should verify that installed ECMs will meet the required standards of service and  the guaranteed annual energy, water, and related cost savings specified in the awarded TO.  Inspections and measurements conducted by the contractor for this post-installation report should be witnessed by the agency, in accordance with FEMP’s "Guide to Government Witnessing and Review of Post-Installation and Annual M&V Activities."  The post-installation report should be reviewed as recommended in FEMP’s “Reviewing Performance Reports for Federal ESPC Projects,” and must be accepted in writing, by the agency.

C.5.4   ECM Commissioning - The contractor shall assure the agency, through the ECM Commissioning, that the ECMs performance achieves facility and/or process performance requirements as set out in the TO.  The ECM Commissioning shall be accomplished through a process of verification and documentation, in accordance with the “Commissioning Guidance for DOE Super ESPCs,” for which the link is located at http://www1.eere.energy.gov/femp/financing/superespcs_espcbasicsp4.html.

C.	ECM Commissioning Report - The contractor shall submit to the agency a Commissioning Report documenting the ECM’s affect upon facility performance requirements in accordance with the Commissioning Plan and agency requirements.

SECTION E INSPECTION AND ACCEPTANCE

## E.1	CLAUSES INCORPORATED BY REFERENCE (FAR 52.252-2)(FEB 1998)

NOTICE:  The following contract clauses pertinent to this section are hereby incorporated by reference:

I.  FEDERAL ACQUISITION REGULATION (48 CFR CHAPTER 1)

CLAUSE

NUMBER     		DATE      	TITLE

52.246-4	AUG 1996	INSPECTION OF SERVICES—FIXED PRICE

52.246-12	AUG 1996	INSPECTION OF CONSTRUCTION

52.246-13	AUG 1996	INSPECTION - DISMANTLING, DEMOLITION, OR REMOVAL OF IMPROVEMENTS

52.246-14	APR 1984	INSPECTION OF TRANSPORTATION

52.246-15	APR 1984	CERTIFICATE OF CONFORMANCE

52.246-16	APR 1984	RESPONSIBILITY FOR SUPPLIES

## E.2	INSPECTION OF INSTALLED ECMs

Each task order (TO) will include specific inspection criteria pertinent to the TO project.  The following general inspection requirements shall apply to each TO, unless otherwise indicated in the TO:

E.2.1	The agency and contractor shall jointly inspect ECMs.  Inspections will be conducted simultaneously, when possible, by both the agency and contractor representatives to facilitate mutual agreement on satisfactory TO ECM performance.

E.2.2	The contractor shall notify the agency Contracting Officer (CO) fifteen (15) working days in advance of ECM installation completion (or such other notification period as may be specified in a TO) by submitting a written request for inspection.  The request shall identify the location, describe the ECMs installed, schedule testing of ECMs for verifying energy savings performance, and recommend dates for inspection (if any).

E.2.3	The agency shall provide written notification to the contractor of scheduled date and time for agency inspection within ten (10) working days after receipt of inspection notification and request (or such other period as may be specified in TO).

E.2.4	Each TO may include additional agency-specific or site-specific inspection and requirements.  The contractor shall review each TO to determine the recommended applicable inspection requirements for that TO.

## E.3	ACCEPTANCE

E.3.1	Partial Project Acceptance - The agency may agree in writing to accept ECM(s) installed and operational prior to completion of the Implementation Period.  If the agency accepts partial project installed ECM(s), it will pay the contractor, prior to full project acceptance, in amounts and frequency specified in Schedule TO-1 (final), column (c).  ECM(s) inspection and testing to verify guaranteed cost savings during the remaining Implementation Period will be conducted and documented by the contractor, and submitted to the agency for acceptance, prior to implementation period contractor payments.  Implementation Period contractor payments shall reduce the project Total Amount Financed (Principal) (Schedule TO-3) and related debt service payments during the TO post-acceptance performance period.

E.3.2	Full Project Acceptance

A.	After installation of all ECMs the agency will notify the contractor in writing of full project acceptance which will constitute the start of the post-acceptance performance period and commencement of contractor payments.  Agency acceptance, for purpose of payment, in accordance with Section G, occurs when the following are completed:

1.	Acceptance by the agency CO of the contractor’s post-installation report;

2.	Acceptance by the agency CO of contractor’s ECM Commissioning Report;

3.	The project inspection is conducted pursuant to Section E.2; and

4.	Submission of additional TO requirements prior to acceptance:

a.	Operations work procedures

b.	Preventive maintenance work procedures

c.	O&M manuals and spare parts lists

d.	Training

e.	As Built Drawings (Record Drawings)

B.	The agency and contractor shall mutually agree on, and specify in the TO, the anticipated schedule for the contractor report submittals and the duration for agency review for acceptance.

G   INVOICING INSTRUCTIONS AND PAYMENT

## G.3	INVOICING INSTRUCTIONS

The contractor shall submit invoices in accordance with the specific instructions provided in each TO issued against this master IDIQ contract.  These instructions will vary by ordering agency, and will include invoice format, invoice contents and any required attachments or enclosures, submission and addressing instructions, etc. required by the TO.

## G.4 	INVOICE SUBMITTAL AND PAYMENT SCHEDULE

G.4.1	Payments to the contractor will commence when acceptance by the agency is obtained as required under Section E.

G.4.2	The frequency of payments, including any partial payments, from the agency to the contractor will be as negotiated and specified in the TO. Options of payment frequency include but are not limited to monthly, quarterly, annual in advance (preferably with debt service only in advance and post-acceptance performance period payments in arrears), or annual in arrears.

## G.5	PAYMENT TO THE GOVERNMENT FOR GUARANTEED ANNUAL SAVINGS SHORTFALL

G.5.1	If the contractor fails to meet the guaranteed annual savings at TO-1 (final) column (e) and as verified by the M&V documents, the agency shall adjust the payment schedule, as necessary, to recover the agency’s overpayments in the previous year and to reflect the lower performance level into the current year.

G.5.2	When the ECM performance level is restored, the agency will adjust the contractor payment schedule accordingly.