## Slide 1: Step 2: Project Options

## Slide 2: Small Group Exercise
Review with a partner what you learned yesterday
Partner 1 explains to Partner 2: Key Concepts (2-3)
  Levelized Cost of Energy (LCOE)
  Offtakers
  Project Roles
  Tax Equity Partnerships
Partner 2 explains to Partner 1: Step 1
  Market and Offtakers
  Initial Site Considerations
  Resources
  Permitting and Regulation

## Slide 3
1
Potential
3
Refinement
5 Operations & Maintenance
2
Design
4
Implementation
2
Options

## Slide 4: Agenda
Final Site Selection
Tribal Role Options
  Business Structure Options
  Project Role Options
  Team Members
Introduction to Financing: Tax Incentives and Up-Front Capital
Partners and Procurement
Permitting
Interconnection and Transmission

## Slide 5
Final site selection
5

## Slide 6: Small Group Exercise
Review permitting, utility rules and SAM output to choose a single site to pursue

## Slide 7
Business Structure options
7

## Slide 8
Importance of Choosing the Right Business Structure
Protect Tribal assets
Preserve Tribal sovereignty
Minimize potential liability
Photo by Brian Hirsch, NREL 20893
Notes: What particular business structure you choose will have a significant impact on whether or not these goals are achieved.

## Slide 9: Business Structure Options for Tribes
Tribal government entities
  Unincorporated instrumentalities
  Political subdivisions
Section 17 corporations
Tribally chartered corporations
State law entities
  State law corporations
  Limited liability companies (LLCs)
Joint venture

## Slide 10: Business Structure: Tribal Government Entities
Option 1: Unincorporated Instrumentalities
Advantages
Easy to form
Management is centralized
Not subject to federal income tax
Same privileges and immunities as Tribal government
Disadvantages
Politics and business are not separated
Assets and liabilities of the enterprise not separated from governmental assets
May preclude equity ownership by outside investors
Option 2: Political Subdivisions
Advantages
Exempt from federal income tax
Retain sovereign immunity
May issue tax-exempt bonds
Ability to form a corporate board
Disadvantages
Timely and costly to form the entity
Not as much flexibility as corporations and LLCs
May deter certain business partners
Source: Office of Indian Energy & Economic Development 2008

## Slide 11: Business Structure: Section 17 Corporations
Tribes can form corporations under Section 17 of the Indian Reorganization Act of 1934
Advantages
Same privileges and immunity as the Tribal government, including Tribal sovereign immunity
Separates the assets and liability of the corporation from Tribal asset
Not subject to federal income tax
Disadvantages
Lengthy timeline to obtain a corporate charter
Corporation must be wholly owned by a Tribe
Example of Section 17 Corp: S&K Technologies, Inc.
  Environmental restoration
  Stream channel reconstruction
  Native plant re-vegetation
  Civil construction
Tour of the Ponnequin Wind Farm. Photo by NREL 09827
Source: Office of Indian Energy & Economic Development 2008 and MacCourt 2010

## Slide 12: Business Structure: Tribally Chartered Corporations
Rooftop PV installation on the Forest Country Potawatomi Tribe administration building. Photo from Forest County Potawatomi Tribe, NREL 20107
Formed by Tribal ordinance or Tribal corporation code
Must select a name and draft articles of incorporation
Best utilized to operate on reservation as an arm of the Tribal government
Example: Ho-Chunk, Inc.
  Information technology
  Construction
  Government contracting
Source: Office of Indian Energy & Economic Development 2008 and MacCourt 2010
Notes: ADVANTAGES: Ease of formation, flexible (can design own governance structure and rules), possible immunity from being sued, separation of corporate assets and liabilities from Tribe.
DISADVANTAGES: Uncertainty of federal tax treatment, not ideal for extensive off-reservation activities, may have to waive sovereign immunity to attract appropriate funding, may not attract certain business partners who want to engage only with state incorporated companies (Renewable Energy Development in Indian Country: A Handbook for Tribes 2010, 31).
Ex. Ho-Chunk, Inc. is a Tribally chartered corporation. Chartered under the laws of the Winnebago Tribe of Nebraska in 1994, Ho-Chunk has grown to be very successful. The company now operates 24 subsidiaries in a diverse range of industries: information technology, construction, government contracting, wholesale distribution, marketing, and retail (Ho-Chunk 2012 http://www.hochunkinc.com/).

## Slide 13: Business Structure: State Law Entities
State Law Corporations and LLCs
(A.K.A. blocker corporations)
Advantages
Quick and easy to organize
Familiar to lenders and potential business partners
Can be used to acquire or merge with an existing state-law entity
Disadvantages
Subject to federal income tax
May not issue tax-exempt debt
Weather Dancer 1 wind project in Alberta, Canada. Photo from Piikuni Utilities Corporation, NREL 13792
Source: Office of Indian Energy & Economic Development 2008 and MacCourt 2010
Notes: Most Tribes avoid forming state-law corporations because they lose the federal tax status of the Tribe, even if wholly owned by a federally recognized Tribe (Office of Indian Energy & Economic Development - Tribal Business Structure Handbook 2008, IV-1). Organizational characteristics vary from state-to-state.
LLCs have the advantage of limited liability like a corporation but are generally taxed like a partnership (not subject to double taxation like corporations are). If a Tribe is the sole member of an LLC, the LLC should receive Tribal tax-exempt status – thus LLCs are more desirable for Tribes than a state law corporation.

## Slide 14: Business Structure: Joint Venture – LLCs or Limited Partnerships
Photo from Bob Springer, NREL 21044
Advantages
Acquire energy project development expertise
Secure project financing
Enjoy benefits of federal incentives (e.g., tax credits)
Disadvantages
Likely loss of sovereign immunity for the joint venture entity
Inability to qualify for certain kinds of financing
Source: Office of Indian Energy & Economic Development 2008 and MacCourt 2010
Notes: The two Joint Venture entity types that are most advantageous for Tribes to utilize are LLCs and Limited Partnerships (LP’s).
ADVANTAGES: They are easy to form, flexible, allow flow-through taxation (Tribe’s share of joint venture income is free of federal tax).
DISADVANTAGES: Likely loss of sovereign immunity for the joint venture entity, inability to qualify for certain kinds of financing, difficulty in dissolving the venture if one party wants to terminate (Office of Indian Energy & Economic Development - Tribal Business Structure Handbook 2008, V-8-V-9).
LLC is most common entity choice for joint ventures between Tribes and non-Tribal businesses – attracted to limited personal liability combined with pass-through tax feature of partnerships.

## Slide 15: Evaluating the Options
Business Structure Option | Simplicity and Quick Formation | Shield Tribal Assets from Business Liabilities | Avoid Federal Income Taxes | Separate Business from Tribal Control | Ability to Secure Financing
Tribal Instrumentality |  |  |  |  | 
Political Subdivision |  |  |  |  | 
Section 17 Corporation |  |  |  |  | 
Tribal Law Corporation |  |  |  |  | 
State Law Corporation |  |  |  |  | 
LLCs/Joint Venture |  |  |  |  | 
LLC (only if Tribe is sole member) |  |  |  |  | 

## Slide 16
Project Role Options
16

## Slide 17: Key Concept: Tribal Role Options
Role | Opportunity | Constraints | Comments
Resource/ Land Owner | Land rent/royalty, taxes. Low risk, known reward, consistent (small) income. | Limited project control. Must provide site access. | Limited upside potential, limited risk
Off-taker/ Energy User | Only pay if project becomes operational; security. | Only available to Tribes that own utility providers. | Still requires utility interconnection agreement. Med risk.
Project Operator/ O&M | Control and self-determination of project; potential for profits (and losses) is minimal | Investors require experience Only consider as a new business (act as operator for multiple projects in a portfolio) | High risk, complex Tribes may be best served by outsourcing
Lender/ Debt Provider | Help finance a project (e.g., cash or New Market Tax Credit (NMTC), or Qualified Energy Conservation Bonds (QECBs)) with lower risk | Requires ready capital May be cost-prohibitive to document and manage a single debt transaction (multiple more cost-effective) | Med-risk, more complex Requires lending knowledge Option for Tribes with limited lands, lots of $
Equity Investor/ Gen. Owner | Provide cash, NMTC or QECB for project development. | Higher risk than debt lending. Requires ready capital, or unique source of capital that provides market advantage (like NMTC). | High risk, more complex Competes with other investments Option for Tribes with limited lands, lots of $
Project Developer | Self-determination of project; potential for profits (and losses) is highest. Tribes with cash on hand don’t need investors, but could still consider engaging tax equity partners. | Investors require experience Only consider as a new business (act as developer for multiple projects in a diverse portfolio) Tribes investing money may not want this high risk/return investment | High risk, complex Tribes may be best served by outsourcing A project pipeline/portfolio mitigates some risks
Notes: Slide 17
There are many different roles that can a Tribe can play. This table describes both the opportunities and general constraints of the different roles.
Quickly, they are
Renewable Resource Owner - Land, rights access to sun, wind, biomass feedstock, geothermal heat; “THE HOST”
Offtaker/energy user – the Tribe will only play this role if it owns a utility; there may be an opportunity for the Tribe to use some power itself, but the primary function is to sell to the utility
Project Operator – that operates and maintains the project
Lender – who provides debt to the project
Equity Investor – Provides both Equity and Tax Equity
Developer - Technical expert on how to secure site, choose EPC, and secure equipment & financing
KEY MESSAGE: The Tribe can play one or several of these roles, depending on the circumstances.

## Slide 18
Team Members
18

## Slide 19: Potential Team Members
Tribal Members
  Leadership, staff, community members
  Attorneys, engineers, professionals
Developer
  Business managers, engineers, permitting specialists, investors, banks, attorneys, accountants, power marketers, procurement specialists, communications, public relations, government relations, corporate finance, project finance, construction managers, O&M specialists, asset managers, etc.
Utility
  Engineers, attorneys, planning specialists, operations specialists, regulatory specialists, finance, accounting, public relations, communications, systems operators, construction and field personnel, maintenance and emergency operations, etc.
Government
  Tribal government, federal, state, local entities, regulating bodies (public utilities commission), Bureau of Indian Affairs, DOE, Federal Energy Regulatory Commission, etc.
Notes: When all is said and done, a lot of people will be involved in the project. In all likelihood, there will be a core team of professionals focused on the project and a more broad team that gets engaged as their expertise or approval is required. The slide, while not exhaustive, provides an overview of the diversity of the project team, and examples of the skill sets that are require to ensure the project’s success.

## Slide 20: Key Success Component
  Identify and select an energy “champion” to shepherd the process
Photo by Dennis Schroder, NREL 21010

## Slide 21: Project Champion’s Role
Project Champion
Employ relevant expertise: legal and finance; technical and construction; power marketing
Ensure all relevant players are engaged in the project at the right time, levels, and roles
Engage Tribal leadership, project, and business management (professionals and staff)
Notes: Like any successful endeavor, there usually one or more project champions who keep the entire stakeholder group moving in the right direction
Depending on the project and the circumstances, the profile of this Project Champion can vary. It may be some one from Tribal leadership, or from Tribal administration or possibly an outside consultant.

## Slide 22: Small Group Exercise
Brainstorm pros and cons of different Tribal roles

## Slide 23
Intro to Financing: Tax Incentives
and Up-front capital
23

## Slide 24: Key Concept: Tax-Equity Partnerships
Tribe can benefit from tax-equity incentives without being taxable
Tribes can partner with third-party tax investors and/or developers to gain this incentive/advantage
  Recent IRS PLR supports Tribal partnerships with third-party tax equity
  Even with IRS ruling, the Tribe needs capital to build a large renewable project
Tax incentives (MACRS and either PTC or ITC) can represent up to half the project value, or reduce project’s capital costs by ~50%
Tribe benefits by offering a more competitive price for energy and RECs from the project to a utility
Notes: Slide 24
Let’s talk for a minute about the Key Concept of Tax Equity Partnerships.
Tribes can benefit from tax-equity incentives without being taxable
Tribes partner with a 3rd party owner, so the tax credits benefit the project.
For large commercial RE projects, the project economics will likely depend on tax incentives, in order to achieve a reasonable payback. Again, federal government tax incentives offered for renewable energy development can represent up to half the value of the project.
Tribes benefit by offering a more competitive price for energy and RECs to a utility
If the Tribe is one of the developers, or one of the equity investors, the Tribe may still have the option to own the project after the useful tax credit life.
You CAN develop a project without a tax equity partner. However, it is unlikely that the economics of a large commercial project will make sense, so there would have to be another compelling reason to skip this type of partnership to give up the tax credit opportunity.
BUT by including a tax equity partner, it puts more cooks kitchen, which means more opinions to consider in all areas of project development

## Slide 25: So Why Seek a Tax-Equity Finance Partner?
Chart: Project Capital Costs
| 3rd Party Owned | Tribe Owned (w/o Partner)
 | 50 | 100
Third-Party-Owned
Tribe-Owned (w/o Partner)
Tax incentives (MACRS and either PTC or ITC) can represent up to half the project value or reduce project’s capital costs by ~50%
Tax incentives can help to achieve a competitive price of power
Many projects also require state-level incentives to be economic
Notes: Slide 25
If your Tribe decides to go for a commercial project to sell power and try to make a decent (not large, but decent) return on the investment, it is imperative to consider partnering with a tax equity investor who would develop and possibly own the project (for a period of time).
Tax incentives are quite generous right now and when combined, they can represent up to half the project value. In other words, the total cost of the project will be half of what it would be if the Tribe paid cash for it. Therefore, securing a tax equity partner can be well worth the challenge of adding partners.
Importantly, the federal incentives are set to make the power from these renewable projects competitive with the price of power, but only in certain locations with the right conditions around the U.S. (with high electricity prices, great renewable resources, streamlined permitting and interconnection processes, or a combination of all of the above). For those projects that are not in the ideal location (which will be most of them), additional state incentives may still be required to make the project work economically.

## Slide 26: Key Concept: Tax-Equity Partnership – Federal Tax Incentives
Production Tax Credit (PTC); payment based on kWh produced
  10-year, 2.3¢/kWh for wind, geothermal, and closed-loop biomass technologies
  “Start construction” before 1/1/2014
Investment Tax Credit (ITC); payment based on % of up-front cost
  One-time 30% or 10% tax credit (depending on technology) of eligible tax basis
  “Placed in service” before 1/1/2017
Geothermal eligible for PTC and ITC; can only take one of them
Cost recovery of plant through depreciation deductions
  Often called “accelerated depreciation”
  Officially called Modified Accelerated Cost Recovery System (MACRS)
Need to pay taxes and have enough of the right kind of tax liability to use
federal tax incentives
Internal Revenue Code
Notes: Slide 26
This slide shows the details of the federal tax credit incentives. As mentioned on slide 14, these tax incentives can represent up to half the project value. Because Tribes do not pay taxes, Tribes are not able to use these tax credits without an investment partner.
  First kind is production tax credit, or PTC and is $.023 (2.3 cents for every kilowatt hour on RE produced). Works for wind, geo, and some biomass (that where the biomass is specifically grown for fuel)
  May expire at end of 2013, though could be extended, or you can qualify by starting construction
  Second type, is investment tax credit, or ITC and it covers 30% or 10% of the upfront capital investment, depending on the technology). Solar currently receives an ITC of 30%.
   Geothermal can take one or other, but not both
The other form of tax advantage is accelerated deprecation, which is a write off, or deduction of the cost of most RE equipment. Although it is not often mentioned, it is one of the key incentives offered to capital investments for renewable or other types of large capital investments

## Slide 27: Step 2: Project Options and Strategies
Financial Capital Sources
Financing structure is highly dependent on capital used for a given project:
  Tribal capital: Tribal investment ($$$) to purchase project equipment
  Tribe-private sector capital sharing: Tribe contributes some resources ($) and partners with third-party capital to leverage tax equity ($$)
  Non-Tribe capital: Developer equity, tax equity, bank debt. Tribe participates in other ways.
Responsibility to generate capital, collect revenues, and monitor returns will vary according to project structure
If all framework elements are fully developed and meet market conditions, the project is ready to attract capital
Notes: Slide 27
As part of the options of the Tribe, it is important to remember, in fact always remember: “how much is this stage going to cost, and how are we going to fund it”. We’ve broadly categorized the types of funding into 3 different levels of financing commitment required by the Tribe:
  Tribal capital – Tribe pays for project outright (BUT NOTE commercial scale projects require tens if not hundreds of millions of dollars of investment, which is why investment partners are usually needed)
  Tribe – private sector capital sharing – where you split the costs between a Tribe and private capital investment; and
  Non-Tribe capital – Tribe contributes resources such as land and possibly some human capital expertise, instead of actual dollars to the project. This is lowest risk, with lowest expected return.

## Slide 28: Small Group Exercise
Role play different characters to better understand debt and equity investment options

## Slide 29
Partners and Procurement
29

## Slide 30: Procurement Process
Negotiate Contracts
Make Selection
Commercial-Scale Projects
Develop and Issue RFP
Potential Project Partners to Procure
  Project Developer
  Engineering Procurement and Construction (EPC) Contractor
  Environmental Permits Contractor
Notes: These partners are responsible for different tasks
  The RFP and contracts will have different provisions, but the process is similar for all three
The following slides detail the procurement of the developer
  In your binder, you can find more information on the EPC and env
In general, the procurement process for facility and commercial scale projects can be broken down into three different categories.
Developing and issuing the RFP;
Selecting a partner and
Negotiating contracts.

## Slide 31: Outline of the RFP Process
Develop RFP
  Timeline: 1 month – 1 year (depends on project scale and site complexity)
  Who creates the RFP: Project leader, contract officer/lawyer, site manager(s), energy manager and technology expert. RFP writers will receive input from utility, Tribal leaders, and stakeholders
  RFP content
Issue RFP
  Tribal networks, federal networks and industry networks
Administer the RFP
  Proposal meeting(s)
  Site tour(s) – can be concurrent with proposal meeting
  Q&A process – ensure all developers get same information
Evaluate Criteria
  Should be a clear process with well defined criteria
  Evaluation panel recommended to consist of an odd number of members (typically 3 to 7)
Award Contract
  Four approaches
Notes: The first step is the Request for proposal process. As has been stated throughout this presentation, the larger the project, the more complex the contracting, so while we’ll walk through the RFP process step by step, such a detailed process will be more relevant for larger projects. A small project, again, 25 kW PV system on a school for example, maybe something more streamlined such as requesting three bids and choosing the best option, will be appropriate.
There are 5 major steps in the RFP process: Developing the RPF itself; Issuing the RFP; Managing and Administering the Process: Establishing a well thought out process and criteria for selecting the winning bidder and finally, awarding the contract. We’ll walk through these steps one by one in the following slides.

## Slide 32: Develop RFP
Key Elements of the RFP
  Type of procurement:
    Purchase
    PPA
    Other finance structure
  Technical specification (scope of work)
  Criteria for evaluating proposals: 3–5 of most important project aspects
    Proposed project solution that meets specified criteria
    System performance guarantee
    Developer experience, track record and customer satisfaction
    Developer financial health/longevity
    Maintenance plan
    Reasonable timelines
    Other
Notes: Developing the RFP
First consider what we are procuring
Develop appropriate technical specifications for the project and the type of procurement.
Developer appropriate evaluation criteria

## Slide 33: Develop RFP (continued)
Key Elements of the RFP
  Description of RFP administration process
    Typically 2–5 months
    Key dates: proposal meeting(s), sites visit(s), proposal due date
    Description of how questions will be handled and answered
  Defining responsible parties
    Who is responsible for permits
    Who is responsible for interconnection agreements
    Who is responsible for applying for incentives
  Any preferences on parties allowed to submit proposals
    Small business
    Minority-owned
    Other
  Land use agreements
    Address site access and land use issues as relevant to ownership model
Notes: Lay out the parameters of the RFP process in the solicitation to bidders addressing all the material issues including timeline for response, site visits, the Q&A procedure, interviews, scoring, ect.
Include in the RPF a clear discussion of which party is responsible for the different development tasks and expenses. If the Tribe is going to handle the permitting, state so. If the Tribe expects the winning bidder to do all the permitting, state so. This allows bids to be compared on a more level playing field.
Are there any preferences or additional points given for different criteria.
What about site access, but during construction as well as long term access.

## Slide 34: Technical Specifications
Define Scope of Work
  What is the project scale
  Type of RE technology
  Site information:
    Location
    Interconnection requirements as known
    Applicable codes and standards
    Roof structure, soils, other (as applicable and available)
    Site prep: fencing, roads, grading limitations, etc.
    Installation requirements: min/max heights of equipment, vegetation mitigation, design standards for structural/electrical
  Equipment minimum standards and warranties
  Expected minimum performance (recommended) or capacity
  Commissioning plan
Notes: As it relates to Technical Specs, based on what path the Tribe has selected, it will either be contracting for particular equipment (the RE installation itself) or for the purchase of electricity through a PPA.
The degree and specificity that each of the topics in the slide are addressed in a given RFP process will vary. For example, if the Tribe is directly purchasing the equipment, then certain things such as equipment warranties will be very important since the Tribe will be the owner.
However, if the RFP is to select a PPA provider, the Tribe will likely put more emphasis on the bidders demonstrated ability to finance the project, how much production the bidder will guarantee, and buy-out options, for example.
When contracting for a PPA, it is common to let the bidder propose the type of equipment that they intend to use if they are selected, rather than have the Host specify a particular brand of module, for example. Of course, if a Tribe is wants to stipulate certain conditions like “made in the USA’ equipment or a certain number of construction jobs have to go to Tribal members, then all of this should be in the RFP.
Regardless, in both cases, the Scope of Work will be a thorough description of the proposed project, the characteristics of the site and a detail overview of what the Tribe is interested in procuring.
Don’t forget O&M. Who is going to perform if; how often; how will warranties be managed if necessary to replace equipment, and how much will it cost.

## Slide 35: Evaluation Criteria
Two Typical Approaches
  Best value:
    Typically 3–5 criteria with weighting based on importance
    Score proposal on each criteria
    Somewhat subjective and can lead to contentious, time-consuming evaluations but good method to capture best value
  Low price, technically acceptable
    Proposals initially stripped of pricing/cost information
    First evaluation determines proposals that meet technical hurdle
    Technically acceptable proposal with lowest cost gets award
    More transparent process but may not capture best value
Notes: Included in the RFP process and the actual RFP is a well thought out process to evaluate bids. The goal is to select the best bidder based on the criteria chosen to guide the selection process and to do so in a transparent way that does not leave the Tribe open to protests from the unsuccessful bidders.
There are two typical approaches.
Best Value which allows criteria other than price to be more heavily weighted
or Low Price, technically acceptable, which starts with technical capabilities, but then is based on the lowest cost among those deemed technically capable.

## Slide 36: Award Contract
Choose One of These Four Typical Approaches
  Award based on proposal
    Awarded solely on merits of proposal
  Award with discussion
    Awarded on proposal but contingent on clarifying discussions
  Award with discussion and negotiation
    Awarded on proposal but contingent on further negotiation
  Award with best proposal
    Best proposals are short-listed
    Short-listed proposals asked for best final proposal revision
    Award based on final proposal revision
Notes: With clear evaluation criteria in place, the contract is then awarded.
In this case, there are four common approaches.
As illustrated in the slide, the award process itself is successively longer as you move down the list. That said, it might also mean that there are less surprises down the line for a contract chosen say for example under the Award with Discussion and Negotiation, then under the Award Based on Proposal.
Tying the award process back to scale, when selecting a contractor for a small, facility scale project, for example, the Award Based on Proposal may be sufficient. However, for a larger, more complex community scale project, follow-up discussions and negotiations might be needed to address bidder questions, tease out unclear information from the bid response and selecting a winner.

## Slide 37: Post-Procurement
Ongoing Monitoring and Maintenance
Project Gets Commissioned
Project Gets Built
Notes: With the award of the contract, the Tribe begins to transition from step 4 to step 5.
The Tribe is now a counterparty to a transaction and here is where the project gets built, contractors get paid, the system gets commissioned, the utility gives the OK to turn it on and electricity begins to be generated.
However, as the Tribe is dealing with long term assets and long term contracts, the project doesn’t end at commissioning. Without diligent attention to on-going operations and maintenance, and other performance related issues, the Tribe may not maximize its investment.

## Slide 38: Summary: Project Procurement and Implementation
Procurement strategy will vary depending on the project scale and financing solution selected
Increasingly more complex for larger projects
Post procurement issues are critical as these are very long term assets and relationships
Notes: Project scale heavily influences the procurement process.
Job isn’t over when the project is commissioned, but rather the Tribe is now either the owner of a RE system or a counterparty to a power purchase agreement; both of which are long term responsibilities.

## Slide 39: Small Group Exercise
Evaluate the RFP responses provided by identifying overall goals and developing values to help rank responses

## Slide 40
Permitting
40

## Slide 41: Permitting
Permitting Example – City Level
Permitting Example – Federal Level
Permitting Checklists and Guide Examples
Hiring a Consultant
Common Missteps and Caveats

## Slide 42
Interconnection and Transmission
42

## Slide 43: What is Interconnection?
“The technical rules and procedures allowing customers to ‘plug in’ to the grid.”
Source: Freeing the Grid 2013. http://freeingthegrid.org/wp-content/uploads/2013/11/FTG_2013.pdf

## Slide 44: Common Interconnection Elements
Application
Designated interconnection utility representative
Generator size thresholds
  Different tracks for generators of certain sizes
  Fast-track procedure for systems smaller than a certain size (generally ~2 MW)
  Technical screens, feasibility studies, etc., for larger, more complex systems
Timelines for each step
Standard agreement between utility and customer

## Slide 45: Database of State Incentives for Renewable Energy
Check DSIRE: http://dsireusa.org

## Slide 46
Interconnection Policies..
www.dsireusa.org / February 2013..
43 States,
+ Washington DC
and Puerto Rico,
have adopted an interconnection policy.
Notes: Numbers indicate system capacity limit in kW. Some state limits vary by customer type (e.g., residential versus non-residential).“No limit” means that there is no stated maximum size for individual systems. Other limits may apply. Generally, state interconnection standards apply only to investor-owned utilities.

## Slide 47: Sample Interconnection Agreement
http://xcelenergy.com/staticfiles/xe/Marketing/Files/NM-Small-Program-%20Interconnection-Agreement.pdf

## Slide 48: Interconnection and Transmission
Required Agreements
General Process for Interconnection
How to Find Utility Rules on Interconnection
Common Missteps and Caveats

## Slide 49: Small Group Exercise
Utility scavenger hunt! Identify the interconnection rules and process for your identified utility and project size

## Slide 50: Commercial-Scale Project Risks – Post Step 2
 | Risks | Risk Assessment Post Step 2
Development | Poor or no renewable energy resource assessment Not identifying all possible costs Unrealistic estimation of all costs Community push-back and competing land use | Finalized resource Reduced Reduced Reduced
Site | Site access and right of way Not in my backyard (NIMBY)/build absolutely nothing anywhere (BANANA) Transmission constraints/siting new transmission | Reduced Reduced Reduced
Permitting | Tribe-adopted codes and permitting requirements Utility interconnection requirements Interconnection may require new transmission, possible NEPA | Reduced Reduced High risk, reduced
Finance | Capital availability Incentive availability risk Credit-worthy purchaser of generated energy | High risk, reduced Reduced Reduced
Construction/ Completion | EPC difficulties Cost overruns Schedule | Low; allocate to EPC or developer
Operating | Output shortfall from expected Technology O&M Maintaining transmission access and possible curtailment | Assumed low, mitigable, or allocatable
Sources: Adapted from Holland & Hart, RE Project Development & Finance & Infocast, Advanced RE Project Finance & Analysis
NOTE: Underlining signifies that the risk assessment outcome changes during the step at hand.
Notes: Slide 50
This slide shows a comparison of the various risks that may emerge out of stage 2 – options analysis. A determination will be needed whether the risk is something that can be acceptable in the project, or can be reduced/eliminated.
As shown, many of the risks were reduced to some degree and a few aspects were finalized – including the resource and the projection of project output. Although the projection may change – for example, you may need to change your equipment or project positioning- in order to deal with later stage aspects, like endangered species.
The key thing to remember is that several of these risk factors must be moved enough down the project development pathway before you will be able to engage a tax equity partner or a debt lender.