## Test Summary
[14 empty] | High = 5 |  | High = 10 - 8
[10 empty] | ê | ê | ê | ê | Medium = 3 |  | Medium = 6 - 4
[6 empty] | Process Owner Due Date: | BKET |  |  | 2021-02-19 | 2021-03-19 | 2021-04-22 | On-Site | Low = 1 |  | Low = 2
Test Description | POC | Process | Guideline | Attr | Test ID | Source | 2021-01-21 | 2021-02-21 | 2021-03-21 | 2021-01-21 | 2021-02-21 | 2021-03-21 | 2021-04-21 | Systemic | Impact | Score | Process Lead Comments
WBS dictionary unsubstantiated (not 1.1.1, X.2) |  | A. Organizing | 1 | A.01 | 01.01.01 | DOE | NA | NA | NA | Flag | Pass | Pass | Flag | 3 | 5 |  | No issues with WBX Dictionary being unsubstantiated.
WBS scope, dictionary <> WAD |  | A. Organizing | 1 | A.01 | 01.01.02 | DOE
CA DB, RAM <> IPMR F1 |  | A. Organizing | 1 | A.01 | 01.02.01 | DOE
WBS index <> BL IMS |  | A. Organizing | 1 | A.01 | 01.02.03 | DOE
WBS dictionary unsubstantiated (1.1.1, X.2) |  | A. Organizing | 1 | A.02 | (N) 01.01.03 | DOE
CA WBS or DB, current <> prior |  | A. Organizing | 1 | A.02 | 01.03.01 | DOE
WBS not further decomposed |  | A. Organizing | 1 | A.02 | 01.04.01 | DOE
DB, IPMR F2 <> dollarized RAM |  | A. Organizing | 2 | A.03 | 02.01.01 | DOE
units % complete, EVMS cost tool <> FC IMS |  | A. Organizing | 3 | A.04 | 03.01.01 | DOE
start or finish dates, EVMS cost tool <> BL IMS |  | A. Organizing | 3 | A.04 | 03.01.02 | DOE
start or finish dates, EVMS cost tool <> FC IMS |  | A. Organizing | 3 | A.04 | 03.01.03 | DOE
start or finish dates, EVMS cost tool <> WAD |  | A. Organizing | 3 | A.04 | 03.01.04 | DOE
DB, EVMS cost tool <> WAD |  | A. Organizing | 3 | A.04 | 03.01.05 | DOE
WBSs by EOC, EVMS cost tool <> FC IMS |  | A. Organizing | 3 | A.04 | 03.01.06 | DOE
labor units, BL IMS <> EVMS cost tool |  | A. Organizing | 3 | A.04 | 03.01.07 | DOE
DB, dollarized RAM <> IPMR F1 |  | A. Organizing | 3 | A.04 | 03.01.08 | DOE
WBS identifier in BL IMS not in EVMS cost tool |  | A. Organizing | 3 | A.04 | 03.01.09 | DOE
completed, EVMS cost tool <> FC IMS |  | A. Organizing | 3 | A.04 | 06.01.03 | DOE
WBS descriptions, dictionary <> CAM |  | A. Organizing | 5 | A.05 | 01.02.02 | DOE
CA does not have just 1 responsible organization |  | A. Organizing | 5 | A.05 | 05.01.01 | DOE
CA is not assigned just 1 WBS in EVMS cost tool |  | A. Organizing | 5 | A.05 | 05.01.02 | DOE
CAM, BCP <> WAD |  | A. Organizing | 5 | A.05 | 05.02.01 | DOE
CA does not have just 1 CAM assigned |  | A. Organizing | 5 | A.05 | 05.03.01 | DOE
CAM or DB, WAD <> dollarized RAM |  | A. Organizing | 5 | A.05 | 05.04.01 | DOE
CA with 3 consecutive SV or CV threshold trips |  | A. Organizing | 5 | A.05 | 05.04.02 | DOE
HDV-CI, index <> BL IMS |  | B. Planning & Scheduling | 6 | B.01 | 06.01.01 | DOE
discrete in EVMS cost tool not in FC IMS |  | B. Planning & Scheduling | 6 | B.01 | 06.01.02 | DOE
100% complete without actual finish |  | B. Planning & Scheduling | 6 | B.02 | 06.02.01 | DOE
> 0% complete without actual start |  | B. Planning & Scheduling | 6 | B.02 | 06.02.02 | DOE
FC IMS with activities out-of-sequence |  | B. Planning & Scheduling | 6 | B.02 | 06.02.03 | DOE
FC IMS actual start or finish date, current <> prior |  | B. Planning & Scheduling | 6 | B.02 | 06.02.04 | DOE
BL IMS not in FC IMS |  | B. Planning & Scheduling | 6 | B.02 | 06.02.05 | DOE
FC IMS in freeze period not in BL IMS |  | B. Planning & Scheduling | 6 | B.02 | 06.02.06 | DOE
FC IMS not in BL IMS |  | B. Planning & Scheduling | 6 | B.02 | 06.02.07 | DOE
BL IMS without relationships |  | B. Planning & Scheduling | 6 | B.03 | 06.03.01 | DOE
FC IMS without relationships |  | B. Planning & Scheduling | 6 | B.03 | 06.03.02 | DOE
BL IMS with SF relationship |  | B. Planning & Scheduling | 6 | B.03 | 06.03.03 | DOE
FC IMS with SF relationship |  | B. Planning & Scheduling | 6 | B.03 | 06.03.04 | DOE
BL IMS with SS or FF relationships |  | B. Planning & Scheduling | 6 | B.03 | 06.03.05 | DOE
FC IMS with SS or FF relationships |  | B. Planning & Scheduling | 6 | B.03 | 06.03.06 | DOE
BL IMS with leads |  | B. Planning & Scheduling | 6 | B.03 | 06.03.07 | DOE
FC IMS with leads |  | B. Planning & Scheduling | 6 | B.03 | 06.03.08 | DOE
BL IMS with lags > 22 work days |  | B. Planning & Scheduling | 6 | B.03 | 06.03.09 | DOE
FC IMS with lags > 22 work days |  | B. Planning & Scheduling | 6 | B.03 | 06.03.10 | DOE
BL IMS with hard constraints |  | B. Planning & Scheduling | 6 | B.03 | 06.03.11 | DOE
FC IMS with hard constraints |  | B. Planning & Scheduling | 6 | B.03 | 06.03.12 | DOE
BL IMS with soft constraints |  | B. Planning & Scheduling | 6 | B.03 | 06.03.13 | DOE
FC IMS with soft constraints |  | B. Planning & Scheduling | 6 | B.03 | 06.03.14 | DOE
BL IMS start or finish dates outside top level schedule |  | B. Planning & Scheduling | 6 | B.04 | 06.04.01 | DOE
FC IMS start or finish dates outside top level schedule |  | B. Planning & Scheduling | 6 | B.04 | 06.04.02 | DOE
FC IMS start or finish dates different from supplemental FC IMSs |  | B. Planning & Scheduling | 6 | B.04 | 06.04.03 | DOE
BL IMS without resources |  | B. Planning & Scheduling | 6 | B.05 | 06.05.01 | DOE
FC IMS without resources |  | B. Planning & Scheduling | 6 | B.05 | 06.05.02 | DOE
BL IMS milestones, SMs, SVTs, and ZBAs with resources |  | B. Planning & Scheduling | 6 | B.05 | 06.05.03 | DOE
FC IMS milestones, SMs, SVTs, and ZBAs with resources |  | B. Planning & Scheduling | 6 | B.05 | 06.05.04 | DOE
resource start or finish, EVMS cost tool <> FC IMS |  | B. Planning & Scheduling | 6 | B.05 | 06.05.05 | DOE
FC IMS SVT with resources and ZBA unsubstantiated |  | B. Planning & Scheduling | 6 | B.05 | 06.05.06 | DOE
BL IMS resource loading not reasonable |  | B. Planning & Scheduling | 6 | B.05 | 06.06.02 | DOE
FC IMS resource loading not reasonable |  | B. Planning & Scheduling | 6 | B.05 | 06.06.03 | DOE
BL IMS > 44 work days |  | B. Planning & Scheduling | 6 | B.06 | 06.06.01 | DOE
FC IMS push test |  | B. Planning & Scheduling | 6 | B.07 | 06.03.15 | DOE
FC IMS pull test |  | B. Planning & Scheduling | 6 | B.07 | 06.03.16 | DOE
BL IMS on longest path |  | B. Planning & Scheduling | 6 | B.07 | 06.03.17 | DOE
FC IMS on longest path |  | B. Planning & Scheduling | 6 | B.07 | 06.03.18 | DOE
BL IMS LOE on longest path |  | B. Planning & Scheduling | 6 | B.07 | 06.07.01 | DOE
FC IMS LOE on longest path |  | B. Planning & Scheduling | 6 | B.07 | 06.07.02 | DOE
BL IMS non-LOE successor with LOE predecessor |  | B. Planning & Scheduling | 6 | B.07 | 06.07.03 | DOE
FC IMS non-LOE successor with LOE predecessor |  | B. Planning & Scheduling | 6 | B.07 | 06.07.04 | DOE
BL IMS with > 15 predecessors |  | B. Planning & Scheduling | 6 | B.07 | 06.07.05 | DOE
FC IMS with > 15 predecessors |  | B. Planning & Scheduling | 6 | B.07 | 06.07.06 | DOE
BL IMS longest path not reasonable |  | B. Planning & Scheduling | 6 | B.07 | 06.07.07 | DOE
FC IMS longest path not reasonable |  | B. Planning & Scheduling | 6 | B.07 | 06.07.08 | DOE
BL IMS total float not reasonable |  | B. Planning & Scheduling | 6 | B.07 | 06.07.09 | DOE
FC IMS total float not reasonable |  | B. Planning & Scheduling | 6 | B.07 | 06.07.10 | DOE
BL IMS with negative total float |  | B. Planning & Scheduling | 6 | B.07 | 06.07.11 | DOE
BL IMS, LOE on longest path |  | B. Planning & Scheduling | 6 | B.07 | 12.01.01 | DOE
FC IMS, LOE on longest path |  | B. Planning & Scheduling | 6 | B.07 | 12.01.02 | DOE
BL IMS no SM or not linked to DOE |  | B. Planning & Scheduling | 6 | B.08 | 06.08.01 | DOE
FC IMS no SM or not linked to DOE |  | B. Planning & Scheduling | 6 | B.08 | 06.08.02 | DOE
BL IMS SM with resources |  | B. Planning & Scheduling | 6 | B.08 | 06.08.03 | DOE
FC IMS SM with resources |  | B. Planning & Scheduling | 6 | B.08 | 06.08.04 | DOE
FC IMS SM remaining duration low |  | B. Planning & Scheduling | 6 | B.08 | 06.08.05 | DOE
BL IMS missing key activities |  | B. Planning & Scheduling | 7 | B.09 | 07.01.01 | DOE
BL IMS push test |  | B. Planning & Scheduling | 6 | B.10 | 08.02.01 | DOE
BL IMS pull test |  | B. Planning & Scheduling | 6 | B.10 | 08.02.02 | DOE
DB, UB, PMB, MR, CBB, NCC, and AUW not aligned (only 8.1.3, X.1) |  | C. Budgeting & Work Authorization | 14 | C.11 | (N) 08.01.04 | DOE
PMB, IPMR F1 <> dollarized RAM |  | C. Budgeting & Work Authorization | 8 | C.01 | 08.01.01 | DOE
DB units, EVMS cost tool <> BL IMS |  | C. Budgeting & Work Authorization | 8 | C.01 | 08.01.02 | DOE
DB, UB, PMB, MR, CBB, NCC, and AUW not aligned (not 8.1.3, X.1) |  | C. Budgeting & Work Authorization | 8 | C.01 | 08.01.03 | DOE
SLPP without scope, schedule, or budget |  | C. Budgeting & Work Authorization | 8 | C.02 | 08.04.01 | DOE
WAD without scope, schedule, or budget by EOC (not 9.1.1, X.3) |  | C. Budgeting & Work Authorization | 9 | C.03 | 09.01.01 | DOE
CA started prior WAD approved |  | C. Budgeting & Work Authorization | 9 | C.04 | 09.02.01 | DOE
WP by EOC not reasonable |  | C. Budgeting & Work Authorization | 9 | C.05 | 09.03.02 | DOE
Discrete WP > 132 days |  | C. Budgeting & Work Authorization | 10 | C.06 | 10.01.01 | DOE
PP and SLPP DB <= 0 |  | C. Budgeting & Work Authorization | 10 | C.06 | 10.02.01 | DOE
PP activities unsubstantiated |  | C. Budgeting & Work Authorization | 10 | C.07 | 10.02.02 | DOE
WP or PP DB <= 0 |  | C. Budgeting & Work Authorization | 10 | C.07 | 10.03.01 | DOE
WP with EVT LOE and non-LOE |  | C. Budgeting & Work Authorization | 10 | C.08 | 10.04.01 | DOE
0-100 > 22 work days |  | C. Budgeting & Work Authorization | 10 | C.08 | 10.06.01 | DOE
schedule or cost time-phased resources <> QBD time-phased resources |  | C. Budgeting & Work Authorization | 10 | C.08 | 10.06.02 | DOE
apportioned unsubstantiated |  | C. Budgeting & Work Authorization | 10 | C.08 | 10.06.03 | DOE
50-50 > 44 work days |  | C. Budgeting & Work Authorization | 10 | C.08 | 10.06.04 | DOE
PP with actual start |  | C. Budgeting & Work Authorization | 10 | C.07 | 10.07.01 | DOE
PP with ACWP or BCWP |  | C. Budgeting & Work Authorization | 10 | C.07 | 10.07.02 | DOE
WBS BOE unsubstantiated |  | C. Budgeting & Work Authorization | 10 | C.07 | 10.08.01 | DOE
CA DB <> WAD budget |  | C. Budgeting & Work Authorization | 11 | C.07 | 11.01.01 | DOE
CA CPI delta discrete and LOE >= 0.1 |  | C. Budgeting & Work Authorization | 12 | C.09 | 12.02.01 | DOE
CA SPI delta discrete and LOE >= 0.1 |  | C. Budgeting & Work Authorization | 12 | C.09 | 12.02.02 | DOE
LOE unsubstantiated |  | C. Budgeting & Work Authorization | 12 | C.09 | 12.03.01 | DOE
CBB - PMB - MR <> 0 |  | C. Budgeting & Work Authorization | 14 | C.10 | 14.01.01 | DOE
DB, change control log <> IPMR F1 |  | C. Budgeting & Work Authorization | 14 | C.11 | 14.03.01 | DOE
UB, change control log <> IMPR F1 |  | C. Budgeting & Work Authorization | 14 | C.11 | 14.03.02 | DOE
AUW unsubstantiated (14.3.3, X.1 & 4 only) |  | C. Budgeting & Work Authorization | 29 | C.12 | 14.03.03 | DOE
NCC + AUW + OTB <> PMB + MR |  | C. Budgeting & Work Authorization | 15 | C.12 | 15.01.01 | DOE
direct costs, EVMS cost tool <> disclosure statement and time card audits |  | D. Accounting Considerations | 16 | D.01 | 16.02.01 | DOE
project ACWPc, EVMS cost tool <> account system |  | D. Accounting Considerations | 16 | D.02 | 16.01.01 | DOE
A without P (cumulative) non-material/overhead |  | D. Accounting Considerations | 16 | D.03 | 16.03.01 | DOE
P without A (cumulative) non-material/overhead |  | D. Accounting Considerations | 16 | D.03 | 16.03.02 | DOE
P without A (incremental) non-material/overhead |  | D. Accounting Considerations | 16 | D.03 | 16.03.03 | DOE
A without P (incremental) non-material/overhead |  | D. Accounting Considerations | 16 | D.03 | 16.03.04 | DOE
P without A (cumulative) non-material/overhead completed |  | D. Accounting Considerations | 16 | D.03 | 16.03.05 | DOE
A without P (incremental) non-material/overhead completed |  | D. Accounting Considerations | 16 | D.03 | 16.04.01 | DOE
EVMS cost tool ACWP <> IPMR F1 ACWP (incremental) |  | D. Accounting Considerations | 17 | D.04 | 17.01.01 | DOE
EVMS cost tool ACWP <> IPMR F2 ACWP (cumulative) |  | D. Accounting Considerations | 18 | D.04 | 18.01.01 | DOE
disclosure statement indirect budgets unsubstantiated |  | E. Indirect Budget & Cost Management | 4 | E.01 | 04.01.01 | DOE
indirect process in place |  | E. Indirect Budget & Cost Management | 13 | E.02 | 13.01.01 | DOE
rates <> EVMS cost tool table or BL IMS or FC IMSs |  | E. Indirect Budget & Cost Management | 13 | E.02 | 13.01.02 | DOE
BCP rates <> EVMS cost tool table |  | E. Indirect Budget & Cost Management | 13 | E.02 | 13.01.03 | DOE
indirect costs unsubstantiated |  | E. Indirect Budget & Cost Management | 19 | E.03 | 19.01.01 | DOE
VAR analysis or actions unsubstantiated |  | E. Indirect Budget & Cost Management | 24 | E.04 | 24.01.01 | DOE
indirect rate thresholds unsubstantiated |  | E. Indirect Budget & Cost Management | 24 | E.04 | 24.02.01 | DOE
VAR, EVMS cost tool <> IPMR F1 |  | F. Analysis & Managerial Reporting | 22 | F.01 | 22.01.01 | DOE
BCWPi not consistent with budget and EVT |  | F. Analysis & Managerial Reporting | 22 | F.01 | 22.02.01 | DOE
VAR without narrative |  | F. Analysis & Managerial Reporting | 23 | F.02 | 23.01.01 | DOE
VAR inadequate |  | F. Analysis & Managerial Reporting | 23 | F.02 | 23.01.02 | DOE
VAR thresholds unsubstantiated |  | F. Analysis & Managerial Reporting | 23 | F.02 | 23.02.01 | DOE
EVMS cost tool <> IPMR F1 CA WBS BCWSi/c, BCWPi/c, ACWPi/c, DB, EAC |  | F. Analysis & Managerial Reporting | 25 | F.03 | 25.01.01 | DOE
EVMS cost tool <> IPMR F1 project BCWSi, BCWPi, ACWPi |  | F. Analysis & Managerial Reporting | 25 | F.03 | 25.01.02 | DOE
EVMS cost tool <> IPMR F2 CA WBS BCWSi/c, BCWPi/c, ACWPi/c, DB, EAC |  | F. Analysis & Managerial Reporting | 25 | F.03 | 25.01.03 | DOE
Monthly EVMS review unsubstantiated |  | F. Analysis & Managerial Reporting | 26 | F.04 | 26.01.01 | DOE
EVMS use unsubstantiated |  | F. Analysis & Managerial Reporting | 26 | F.04 | 26.01.02 | DOE
VAR analysis or corrective actions unsubstantiated |  | F. Analysis & Managerial Reporting | 26 | F.04 | 26.02.01 | DOE
EAC < ACWPc |  | F. Analysis & Managerial Reporting | 27 | F.05 | 27.01.01 | DOE
EAC unsubstantiated |  | F. Analysis & Managerial Reporting | 27 | F.05 | 27.01.02 | DOE
ETC missing |  | F. Analysis & Managerial Reporting | 27 | F.05 | 27.02.01 | DOE
ETC finish date, EVMS cost tool <> FC IMS |  | F. Analysis & Managerial Reporting | 27 | F.05 | 27.02.02 | DOE
ETC labor units, EVMS cost tool <> FC IMS |  | F. Analysis & Managerial Reporting | 27 | F.05 | 27.03.01 | DOE
abs(CPIc – EAC TCPIc) > 0.1 |  | F. Analysis & Managerial Reporting | 27 | F.05 | 27.03.02 | DOE
direct and indirect rates not correctly applied |  | F. Analysis & Managerial Reporting | 27 | F.05 | 27.03.03 | DOE
annual comprehensive EAC unsubstantiated |  | F. Analysis & Managerial Reporting | 27 | F.05 | 27.04.01 | DOE
MR and UB distributed (14.3.3, X.3 with MR) |  | G. Change Control | 28 | G.01 | (N) 14.03.04 | DOE
AUW unsubstantiated (14.3.3, X.2 only) |  | G. Change Control | 28 | G.02 | (N) 14.03.05 | DOE
Change implementation delayed |  | G. Change Control | 28 | G.02 | 28.01.01 | DOE
UB distribution delayed |  | G. Change Control | 28 | G.02 | 28.01.03 | DOE
contingency usage not documented |  | G. Change Control | 28 | G.02 | 28.01.04 | DOE
AUW partially implemented |  | G. Change Control | 28 | G.02 | 28.02.01 | DOE
DB Change unsubstantiated by SD (28.3.1, X.1 only) |  | G. Change Control | 28 | G.02 | (N) 28.03.02 | DOE
change implemented prior approval or not implemented |  | G. Change Control | 32 | G.02 | 28.01.02 | DOE
CBB or TAB, IPMR F1 <> IPMR F3 |  | G. Change Control | 32 | G.02 | 32.01.01 | DOE
CBB with contingency usage unsubstantiated |  | G. Change Control | 32 | G.02 | 32.01.02 | DOE
MR, change control log <> IMPR F1 |  | G. Change Control | 29 | G.03 | 14.02.01 | DOE
DB Change unsubstantiated (28.3.1, X.2 only) |  | G. Change Control | 29 | G.03 | 28.03.01 | DOE
BCWS change unsubstantiated |  | G. Change Control | 29 | G.03 | 29.01.01 | DOE
CBB change, IPMR F1 <> change control log |  | G. Change Control | 29 | G.03 | 29.01.02 | DOE
BCWS profile changes unsubstantiated |  | G. Change Control | 29 | G.03 | 29.01.03 | DOE
PMB change unsubstantiated |  | G. Change Control | 29 | G.03 | 29.02.01 | DOE
DB change unsubstantiated |  | G. Change Control | 29 | G.03 | 29.02.02 | DOE
MR transaction unsubstantiated |  | G. Change Control | 29 | G.03 | 29.03.01 | DOE
BCWSi < 0 unsubstantiated |  | G. Change Control | 30 | G.04 | 30.01.01 | DOE
BCWPi < 0 unsubstantiated |  | G. Change Control | 30 | G.04 | 30.01.02 | DOE
ACWPi < 0 unsubstantiated |  | G. Change Control | 30 | G.04 | 30.01.03 | DOE
CBB log, current <> prior <> 2 prior |  | G. Change Control | 31 | G.05 | 31.01.01 | DOE
OTB not approved by DOE |  | G. Change Control | 31 | G.05 | 31.01.02 | DOE
change implemented prior DOE authorization |  | G. Change Control | 31 | G.05 | 31.01.03 | DOE
OTB unsubstantiated |  | G. Change Control | 31 | G.06 | 08.03.01 | DOE
A without P (cumulative) discrete material |  | H. Material Management | 21 | H.01 | 21.01.01 | DOE
P without A (cumulative) discrete material |  | H. Material Management | 21 | H.01 | 21.01.02 | DOE
P without A (incremental) discrete material |  | H. Material Management | 21 | H.01 | 21.01.03 | DOE
A without P (incremental) discrete material |  | H. Material Management | 21 | H.01 | 21.01.04 | DOE
A without P (incremental) discrete material completed |  | H. Material Management | 21 | H.01 | 21.01.05 | DOE
HDV-CI not negotiated |  | H. Material Management | 21 | H.02 | 21.02.01 | DOE
HDV-CI LOE |  | H. Material Management | 21 | H.02 | 21.02.02 | DOE
Material EVT unsubstantiated |  | H. Material Management | 21 | H.02 | 21.02.03 | DOE
material accounting system lacks accountability |  | H. Material Management | 21 | H.03 | 21.03.01 | DOE
material price/usage unsubstantiated |  | H. Material Management | 21 | H.04 | 21.04.01 | DOE
material accounting system unsubstantiated |  | H. Material Management | 20 | H.05 | 20.01.01 | DOE
Subcontractor flow down |  | I. Subcontract Management | 1 | I.01 | (N) 03.02.04 | DOE
HDV-CI not identified |  | I. Subcontract Management | 1 | I.02 | 01.04.02 | DOE
subcontractor or inter-organization work unsubstantiated |  | I. Subcontract Management | 2 | I.02 | 02.02.01 | DOE
subcontractor BCWPc, ACWPc, DB, and EAC, BL IMS <> EVMS cost tool |  | I. Subcontract Management | 3 | I.02 | 03.02.01 | DOE
start or finish dates, subcontractor schedule <> BL IMS |  | I. Subcontract Management | 6 | I.02 | 03.02.02 | DOE
start or finish dates, subcontractor schedule <> FC IMS |  | I. Subcontract Management | 6 | I.02 | 03.02.03 | DOE
BL IMS missing key subcontractor activities |  | I. Subcontract Management | 6 | I.02 | 06.04.04 | DOE
Subcontractor Integration |  | I. Subcontract Management | 27 | I.02 | (N) 03.02.05 | DOE
EVMS use unsubstantiated |  | I. Subcontract Management | 26 | I.03 | (N) 26.01.03 | DOE
Risk identification |  | J. Risk Management | 6 | J.01 | (N) 06.09.03 | DOE
risks, index <> BL IMS |  | J. Risk Management | 6 | J.02 | 06.09.01 | DOE
risks, index <> FC IMS |  | J. Risk Management | 6 | J.02 | 06.09.02 | DOE
most likely EAC unsubstantiated |  | J. Risk Management | 6 | J.02 | 27.05.01 | DOE
best, likely, and worst case EACs unsubstantiated |  | J. Risk Management | 6 | J.02 | 27.05.02 | DOE
IPMR F1 EACs <> EAC reported to leadership or DOE |  | J. Risk Management | 6 | J.02 | 27.05.03 | DOE
[7 empty] | BKET |  |  | REVIEW TEAM
[7 empty] | JAN | FEB | MAR | JAN | FEB | MAR
[6 empty] | TOTAL Pass | 0 | 0 | 0 | 0 | 1 | 1
[7 empty] | 0% | 0% | 0% | 0% | 0.4975% | 0.4975%
[6 empty] | TOTAL Flag | 0 | 0 | 0 | 1 | 0 | 0
[7 empty] | 0% | 0% | 0% | 0.4975% | 0% | 0%
[6 empty] | TOTAL Not Perf | 1 | 1 | 1 | 0 | 0 | 0
[7 empty] | 0.4975% | 0.4975% | 0.4975% | 0% | 0% | 0%
[6 empty] | TOTAL | 1 | 1 | 1 | 1 | 1 | 1