## Cur Perf
Current Performance on Projects with Approved Baselines
Program | PARSID | DOE Project Number | Project Name | RYG Overall | Current Critical Decision | Original Approved Cost ($) | Original Completion Date | Rebase | Rebaselined Project Cost ($) | Rebaselined Completion Date | Site
EM | 390 | 01-D-416 | Waste Treatment and Immobilization Plant (WTP) | Red | CD3 | 5781000000 | 2011-07-31 | 3 | 18524000000 | 2027-09-30 | ORP
EM | 1021 | 14-D-403 | Outfall 200 Mercury Treatment Facility | Red | CD3 | 224000000 | 2025-09-30 |  |  |  | Oak Ridge
EM | 1024 | 15-D-411 | Safety Significant Confinement Ventilation System (WIPP) | Yellow | CD3 | 288000000 | 2022-11-30 | 1 | 494000000 | 2026-06-30 | Carlsbad
EM | 1064 | 15-D-412 | Utility Shaft, WIPP | Green | CD3 | 196985000 | 2023-12-31 | 1 | 288000000 | 2026-11-30 | Carlsbad
EM | 1090 | 20-U-401 | On-Site Waste Disposal Facility - Infrastructure Construction | Green | CD3 | 373000000 | 2027-09-30 |  |  |  | Portsmouth
EM | 1129 | OH-WV-0040.C2.2 | Main Plant Process Building | Yellow | CD3 | 206000000 | 2025-07-31 |  |  |  | West Valley
EM | 1133 | 20-D-401 | Saltstone Disposal Unit #10, 11, 12 | Green | CD3 | 496000000 | 2030-07-08 |  |  |  | SRS
EM | 1156 | 20-D-402 | Advanced Manufacturing Collaborative Facility (AMC) | Green | CD3 | 75127000 | 2025-06-30 |  |  |  | SRS
EM | 1197 | 19-D-701 | K Area Argus | Red | CD3 | 79400000 | 2028-03-31 |  |  |  | SRS
EM | 1245 | OR-0041.C3.2 | Ground Water Field Demonstration | Green | CD3 | 80000000 | 2026-06-30 |  |  |  | Oak Ridge
EM | 1262 | OR-0041.IFDP.C1 | Alpha-2 Complex Demolition | Green | CD3 | 92000000 | 2028-10-31 |  |  |  | Oak Ridge
|  | Red | Project is expected to breach its performance baseline cost, schedule, or scope.
RYG- Monthly Overall Assessment |  | Yellow | Project is at risk of breaching its performance baseline cost, schedule, or scope.
|  | Green | Project is expected to meet its performance baseline cost, schedule, or scope.