## Completed Projects
Completed Projects
Site | Project Type | PARSID | Project Name | Approved Budget ($) | Actual Cost ($) | Completion Date Approved | Completion Date Actual | Cost Success | Schedule Success | Complete Scope
ETTP | Decontamination and Decommissioning | 1044 | K-27 Demolition Project | 98201000 | 59500000 | 2018-12-31 | 2017-09-25 | Yes | Yes | Yes
|  | *1097 | Nuclear Facility D&D - ETTP (Program) | 275685000 | 200436000 |  | 2019-09-25 | Yes | No | Yes
|  | 897 | K-25 D & D | 479400000 | 1107000000 | 2017-09-30 | 2015-01-09 | No | Yes | Yes
|  | 1125 | Poplar Creek Area Facility Demolition Project | 95570000 | 89000000 | 2019-09-30 | 2019-09-25 | Yes | Yes | Yes
|  | 1136 | Technetium-99 Contamination Remedial Action Project | 94200000 | 53000000 | 2022-05-30 | 2020-07-28 | Yes | Yes | Yes
KAPL | Decontamination and Decommissioning | **688 | Nuclear Facility D&D - Separations Process Research Unit | 78600000 | 225400000 | 2012-09-30 | 2020-06-18 | No | No | No
Oak Ridge | Decontamination & Decommissioning | 653 | K-25 Decontamination and Decommissioning Project | 479400000 | 1107000000 | 2017-09-30 | 2015-01-09 | No | Yes | Yes
ORP | Facility Construction | 1178 | Tank-Side Cesium Removal System Demonstration Subproject | 164000000 | 135000000 | 2022-07-25 | 2022-04-12 | Yes | Yes | Yes
Notes | Projects that are under $50M and completed before 2015 are exluded from this table. |  | *1097- Project was cancelled after completion of initial work. Zone 2 K-31/K-33 Area Remedial Action Project, and the transfer of Poplar Creek Area Facility Demo Project to PARS 1125. The remaining CD-1 Projects each have a total project cost below $50M and do not require further reporting in PARS II. | **688-KPP 3, Ship approximately 50 cubic meters of transuranic waste by September 2011, was not completed by CD-4. Approximately, 7.5 cubic meters of transuranic waste is in storage, awaiting shipment to another site for processing prior to disposal to the Federal Repository and the turnover of land back to the landlord.
Completed Projects
Site | Project Type | PARSID | Project Name | Approved Budget ($) | Actual Cost ($) | Completion Date Approved | Completion Date Actual | Cost Success | Schedule Success | Complete Scope
Portsmouth | Demolition | 1163 | X-326 Process Building Demolition Project | 160000000 | 131500000 | 2025-10-31 | 2024-07-03 | Yes | Yes | Yes
| Facility Construction | 1047 | On-Site Waste Disposal Facility - Initial Infrastructure & Cells 1, 4 & 5 Liner Construction | 285000000 | 247800000 | 2024-05-31 | 2022-08-16 | Yes | Yes | Yes
Richland | Decontamination and Decommissioning | 402 | Plutonium Finishing Plant (PFP) Decontamination and Dismantlement - ARRA Base | 330200000 | 343000000 | 2011-09-30 | 2020-04-10 | Yes | No | Yes
|  | 673 | Nuclear Facility D&D - River Corridor Closure Project | 2251500000 | 1850000000 | 2019-09-30 | 2018-11-27 | Yes | Yes | Yes
| Demolition | 1043 | Plutonium Finishing Plant Demolition Project | 72600000 | 204000000 | 2018-08-31 | 2022-01-19 | No | No | Yes
| Restoration or Remediation | 1011 | KW Basin Sludge Removal Project | 311000000 | 291000000 | 2019-11-30 | 2018-06-04 | Yes | Yes | Yes
SRS | Facility Construction | 389 | Salt Waste Processing Facility (SWPF) | 900000000 | 2260000000 | 2013-11-30 | 2020-08-17 | No | No | Yes
|  | 538 | Saltstone Disposal Unit #6 (SDU6) | 143166420 | 121700000 | 2018-11-30 | 2017-07-18 | Yes | Yes | Yes
|  | 1068 | Saltstone Disposal Unit #7 (SDU7) | 159000000 | 127000000 | 2022-03-31 | 2021-07-21 | Yes | Yes | Yes
|  | 1120 | Saltstone Disposal Units 8 and 9 | 280000000 | 217700000 | 2024-09-30 | 2024-03-19 | Yes | Yes | Yes
| Restoration or Remediation | 1033 | D-Area Ash Project | 74200000 | 68800000 | 2020-07-31 | 2019-06-10 | Yes | Yes | Yes
Notes | Projects that are under $50M and completed before 2015 are exluded from this table.